## Sheet1
Meeting date: | Time: | Location: | Next meeting: | Uploaded? | Progress achieved: | Participants
2024-03-22 | 2pm | MS Teams | 2024-03-25 | Yes
2024-03-25 | 9am | 47 Tipuana Road | 2024-04-06 | Yes | Each worked with different components and tried to get them working
2024-04-06 | 9am | 47 Tipuana Road | 2024-04-11 | Yes | Got speakers working, integrated with gyro, lights working, sewed gyro into fabric
2024-04-12 | 8am | WIL lecture, campus | 2024-04-19 | No | Updated sprint 1 document, started sprint 2 document
2024-04-19 | 8am | WIL lecture, campus | 2024-04-26 | No | Checked sprint 1 and sprint 2 - gave Sarina conductive fabric
2024-04-26 | 8am | WIL lecture, campus | 2024-06-02 | No
2024-06-02 | 10am | 47 Tipuana Road | 2024-06-05 |  | Got gyroscope working to detect a jump with speakers notifying the user - prototype progress
2024-06-05 | 11:30am | 47 Tipuana Road | 2024-06-09 | Yes | Fixed prototype. Discussed mid-year presentation for 6 June | 4 - Tariq absent
2024-06-09 | 10am | 47 Tipuana Road | 2024-06-17 | No | Attempting to add a left and right jump to the prototype
2024-06-17 | 10am | 47 Tipuana Road | 2024-06-19 | No | Worked on prototype for Sarina, attempted to get the wifi module to spin up wifi so a phone can connect, and sewed in components on the cape
2024-06-19 | Online | Online | 2024-07-29 | No | Decided team members for SATNAC
2024-07-29 | 1pm | 47 Tipuana Road | 2024-07-31 | No | ESP32 spun up bluetooth and communicating to mobile terminal, heart rate sensor working | 4 - Tariq absent
2024-07-31 | 10am | 47 Tipuana Road | 2024-08-02 | no | refinement
2024-08-02 | 10am | 47 Tipuana Road | 2024-08-07 | No | Accelerometer test
2024-08-07 | 10am | 47 Tipuana Road | 2024-08-14 | No | SATNAC concept poster, heart pulse with accelerometer and bluetooth
2024-08-14 | 10am | 47 Tipuana Road | 2024-08-30 | No | LED incorporation with bluetooth, Test week next week
2024-08-30 | 10am | 47 Tipuana Road | 2024-09-04 | No | General check in, SATNAC prep, buy battery holders, mobile app updates
2024-09-04 | 10am | 47 Tipuana Road | 2024-09-06 | no | bought batteries, worked with power sources
2024-09-06 | 10am | 47 Tipuana Road | 2024-09-11 |  | Booked SATNAC, did satnac masterclass work, satnac meeting | 4 - Tariq absent
2024-09-11 | 10am | 47 Tipuana Road | 2024-09-13 |  | More cape work | 4 - Tariq absent
2024-09-13 | 10am | 47 Tipuana Road | 2024-09-16 |  | documentation, cape progress with ESP32 | esp32
2024-09-16 | 11am | 47 Tipuana Road | 2024-09-17 |  | SATNAC documentation, gyro testing
2024-09-17 | 10am | 47 Tipuana Road | 2024-09-18 |  | SATNAC documentation, cape testing
2024-09-18 | 10am | 47 Tipuana Road | 2024-10-23 |  | satnac submission date | 3 - Tariq, James sbsent
2024-10-23 | 8am | Campus | 2024-10-30 |  | build battery source with Sarina | 3 - Tariq, James sbsent
2024-10-30 | 10am | 47 Tipuana Road | 2024-11-06 |  | cape tests with LED | 3 - Ethan, Mishka absent
2024-11-06 | 10am | 47 Tipuana Road | 2024-11-08 |  | WIL documentation udpate, update cape, API push
2024-11-08 | 11am | 47 Tipuana Road | 2024-11-11 |  | WIL documentation, gyro update, mobile app
2024-11-11 | 10am | 47 Tipuana Road | 2024-11-13 |  | cape testing, WIL documentation
2024-11-13 | 10am | 47 Tipuana Road | 2024-11-14 |  | Circle CI and pipelines push
2024-11-14 | 10am | Campus | 2024-11-18 |  | documentation, cape progress with ESP32 | 2 - Chris, James, Tariq absent
2024-11-18 | 10am | 47 Tipuana Road | 2024-11-19 |  | cape testing, WIL documentation
2024-11-19 | 10am | 47 Tipuana Road | 2024-11-20 |  | cape testing, WIL documentation
2024-11-20 | 10am | 47 Tipuana Road | 2024-11-21 |  | cape testing, WIL documentation due
2024-11-21 | 10am | 47 Tipuana Road | 2024-11-22 |  | cape testig, scripts
2024-11-22 | 10am | 47 Tipuana Road | 2024-11-23 |  | presentation practice
2024-11-23 | 10am | 47 Tipuana Road | 2024-11-24 |  | presentation practice
2024-11-24 | 10am | 47 Tipuana Road | 2024-11-25 |  | presentation practice
2024-11-25 | 8am | Campus | None |  | presentation day